## Slide 1: DataCapture Project — Steering Committee
Project status by component
October 2026

## Slide 2: Executive summary
34 / 36
Requirements spec
34 done
1 not started
1 not provided
31 / 36
Development
31 done
1 in progress
3 not started
1 not provided
3 / 36
Testing
3 done
32 not started
1 not provided
Component
Spec
Dev
Test
Management access for users & roles (1)
1/1
1/1
1/1
Communication between DataCapture and ABBY (6)
5/6
2/6
0/6
Communication between DataCapture and Algo (1)
1/1
1/1
1/1
Transverse technical (1)
1/1
1/1
1/1
Communication between DataCapture and Finstar (9)
9/9
9/9
0/9
Document preprocessing & routing (10)
10/10
10/10
0/10
Standard format data extraction (2)
2/2
2/2
0/2
Free format data extraction (2)
2/2
2/2
0/2
Post extraction treatment (3)
3/3
3/3
0/3
Extraction log & reporting (1)
0/1
0/1
0/1
Notes: Component dot = green if all items done, orange if partially done, red if nothing done. Figures = items done / total.

## Slide 3: Status board — Access, ABBY, Algo & transverse
Done
In progress
Not started
Status not provided
Jira
Spec
Dev
Test
Management access for users & roles
Management access for the users & roles
XXXX
Communication between DataCapture and ABBY
Get token to access APIGEE
XXXX
Send financial documents to ABBY
XXXX
Get financial extraction result
XXXX
Get extraction status progress
XXXX
Implementation of data extraction workflow
XXXX
Duplicated codes managing rule
XXXX
Communication between DataCapture and Algo
API for communication between Algo and DataCapture
XXXX
Transverse technical
Design the database structure
XXXX

## Slide 4: Status board — Communication with Finstar
Done
In progress
Not started
Status not provided
Jira
Spec
Dev
Test
Communication between DataCapture and Finstar
Extract Status API
XXXX
Send results to Finstar
XXXX
Creation & implementation of upload API – SAFIR documents
XXXX
Rejection codes to communicate with Finstar
XXXX
Include extraction source in result file
XXXX
Return standard JSON format results to Finstar
XXXX
Standard JSON structure and format
XXXX
Communication of confidence scores and position (by data and average)
XXXX
Detect the statutory auditor's report in financial statements
XXXX

## Slide 5: Status board — Document preprocessing & routing
Done
In progress
Not started
Status not provided
Jira
Spec
Dev
Test
Document preprocessing & routing
Identify the data to be extracted and remove useless pages
XXXX
Generate a rejection message (document incomplete)
XXXX
Detect the mandatory pages by code (standard documents)
XXXX
Generate a rejection message (document not accepted)
XXXX
Detect the mandatory pages by title (free format)
XXXX
Update submission with preprocessing results
XXXX
Identify the document type and its routing
XXXX
Create a UI to test the classification algorithm
XXXX
Filter pages (mandatory & optional pages)
XXXX
Unify output of matched pages
XXXX

## Slide 6: Status board — Data extraction, post-treatment & reporting
Done
In progress
Not started
Status not provided
Jira
Spec
Dev
Test
Standard format data extraction
Identify confidence score calculation rules (standard formats)
XXXX
Extract the data from native & standard PDFs
XXXX
Free format data extraction
Identify the sections to be extracted (free formats)
XXXX
Identify confidence score calculation rules (free formats)
XXXX
Post extraction treatment
Transformation rules of 2144 & 2139
XXXX
Define the storage steps and database objects
XXXX
View the extracted data
XXXX
Extraction log & reporting
Extraction log & reporting (scope to be defined)
XXXX

## Slide 7: Points of attention and next steps
1
Points of attention
ABBY: development not started on APIGEE token and document sending
Get financial extraction result: development in progress
Extraction log & reporting: not yet specified
Testing: 32 of 36 items not started
2
Achievements
Requirements specified for 34 of 36 items
Development completed for 31 items
Fully tested: users & roles access, Algo API, database structure
3
Next steps
Complete ABBY development (token, sending, extraction result)
Launch test campaign on Finstar, preprocessing and extraction items
Specify the extraction log & reporting scope
Fill in the Jira references